## Sheet1
AISC1006 | Group A
Telecom Churn Prediction | Progress report
Team Members
Saraka Sahaswin | sarakasahaswintha@loyalistcollege.com
Maaz Rehan | mohamedmaazrehan@loyalistcollege.com
Fatemi Lokhandwala | fatemisadikbhailo@loyalistcollege.com
Vandit Kalathiya | vanditkalathiya@loyalistcollege.com
Comfort | comfortirohaonuoh@loyalistcollege.com
Dhiraj Dahal | dhirajdahal@loyalistcollege.com
Gaurav Singh Rawat | gauravsinghrawat@loyalistcollege.com
Rahul Batherikal | rahulbatherikal@loyalistcollege.com
| Week 01 | Week 2 | Week 3 | Week 4 | Week 5
Saraka Sahaswin | Individual Project Identification | Dataset Discovery | GIT commands guidance and documentation | Presentation preparation & attribute analysis(Partner,Dependents,tenure) | Dataset analysis, Missing values identification
Maaz Rehan | Individual Project Identification | Dataset Discovery | GIT Repo creation and python libraries | Attribute introduction,analysis and presentation preparation | Dataset analysis, Missing values identification
Fatemi Lokhandwala | Individual Project Identification | Dataset Discovery | GIT installation and walkthrough | Attribute analysis(gender & seniorCitizen) | Dataset analysis, Missing values identification
Vandit Kalathiya | Individual Project Identification | Dataset Discovery | Anaconda installation and introduction | Attribute analysis(Contract & PaperlessBilling) | Dataset analysis, Missing values identification
Comfort Onuoha | Individual Project Identification | Dataset Discovery | Dataset attributes identification | Attribute analysis(DeviceProtection & TechSupport) | Dataset analysis, Missing values identification
Dhiraj Dahal | Individual Project Identification | Dataset Discovery | Reporting and Documentation | Attribute analysis(OnlineSecurity,OnlineBackup) | Dataset analysis, Missing values identification
Gaurav Singh Rawat | Individual Project Identification | Dataset Discovery | Project scope identification | Presentation Preparation & Dataset understanding(PhoneService,MultipleLines,InternetService) | Dataset analysis, Missing values identification
Rahul Batherikal | Individual Project Identification | Dataset Discovery | Data collection | Dataset analysis and visualization(StreamingTV,StreamingMovies) | Dataset analysis, Missing values identification
Notes | On Week 1, Each member came up with 2 project ideas and presented to the group to decide on the final project idea. | On week 2, The project was decided on and the team was introduced to the dataset and its attributes as well as the introduction to kaggle. | On Week 3, Each member was introduced to the dataset,GitHub, Kaggle and Jupyter notebook. | Week 4, Dataset was divided among each member and was introduced to the basics of Jupyter notebook, Pandas and matplotlib. Presentation was created by the team with everybody present, so that we could brainstorm and collaborate to get suggestions. | Week 5, Dataset analysis was continued while learning how to use different python libraries. Target variable imbalance was identified on the dataset.